## Read me
Site diary template
A site diary kept as one row for each job each day, so a week, a job or every delay can be filtered in seconds. Free to use and to share. From ivankristo.com.
How to use it
1. Diary sheet: one row for each job on each working day, written the same day. Short entries are fine: numbers for labour, a list for plant and deliveries.
2. Write down what happened, not what was planned: who was on site, what arrived, what the weather did, which instructions came in and from whom, and anything that stopped or slowed the work and why.
3. Photos: note where they are kept (a folder, a phone album) so they can be found against the date.
4. To look back: filter the Job column for one job, or the Delay column for every day something went wrong.
Why the same day
A diary is the record everyone asks for when a delay, a variation or an accident is argued later. Entries made on the day, by the person who was there, carry weight; a week written up from memory on Friday does not. Commentary published by NEC describes site diaries that record daily resources, progress, stoppages and the reasons for them as indispensable for showing cause and effect.
Questions, or a register that runs itself: ivan@ivankristo.com

## Diary
Date | Day | Job | Weather (morning / afternoon) | Own labour on site | Subcontractors (who, how many) | Plant on site | Deliveries (what, ticket no.) | Work done | Instructions received (what, from whom) | Delays or stoppages and why | Visitors and inspections | Accidents or near misses | Photos kept at | Written by